## TEMPLATE
ID Ref. | Page | Page Sub-Component | Code Ver. | Category | Approach | Pass Criteria | Fail Criteria | Test Case ID | Manager | Test Engineer | Tester
01_01 | Volunteer | Desktop | 1 | LAYOUT | ensure that layout load correctly. Static test will check for placement and alignment of all components as they are designed in the wireframes | all components are loaded according to wireframes | colour or font attributes are not as specificed. Incorrect content displayed, incorrect layout of components | FF_volunteer_1 | Sean Doyle | Kyle Cheung | Sandra Kupfer
01_02 | Volunteer | Mobile | 1 | LAYOUT | ensure that layout load correctly for the mobile view. Static test will check for placement and alignment of all components as they are designed in the wireframes. Ensure that both landscape and portrait mode work properly | all components are loaded according to wireframes. Layout properly changes when switched from landscape to portrait mode | colour or font attributes are not as specificed. Incorrect content displayed, incorrect layout of components, layout doesnt change when switching modes | FF_volunteer_2 | Sean Doyle | Kyle Cheung | Amanda Elias
01_03 | Volunteer | Application button | 1 | FUNCTIONALITY | As an anonymous user ensure that all events needing a volunteer are listed. When the apply now button is clicked the user should be redirected to an application form | the user is able to see and click on the apply now button. After pressing the button the user is redirected to an application form | The user is unable to see listed events. Clicking on the apply now button does not redirect properly. | FF_volunteer_3 | Sean Doyle | Kyle Cheung | Wafa Mustafa
01_04 | Volunteer | Application Form | 1 | FUNCTIONALITY | Ensure that all events are loaded properly. All information is correct. | All events needing volunteers are listed. All information is valid and correct | There is missing information or incorrect values. Some or all events are not listed | FF_volunteer_4 | Sean Doyle | Kyle Cheung | Mihoko Schick
01_05 | Volunteer | Admin Dash | 1 | FUNCTIONALITY | ensure that as an administrator. A user is able to view all volunteer applications as well as edit, view, delete, and approve them | A user is able to edit, delete, view, and approve volunteers. All information is displayed properly, all edited and approved applications are updated correctly. | a user is unable to edit, delete, view, or approve applications or incorrect values are displayed when submitted | FF_volunteer_5 | Sean Doyle | Kyle Cheung | Farshan Aslam
01_06 | Volunteer | Chrome | 1 | COMPATABILITY | dynamic test. Load the website in chrome and ensure that the layout, fonts and sizes are identitcal to the wireframes | all components load properly. All components and sizes are according to the wireframes | colour or font attributes are not as specified. Incorrect content displayed. Incorrect sizing or layout | FF_volunteer_6 | Sean Doyle | Kyle Cheung | Sandra Kupfer
01_07 | Volunteer | Firefox | 1 | COMPATABILITY | dynamic test. Load the website in firefox and ensure that the layout, fonts and sizes are identitcal to the wireframes | all components load properly. All components and sizes are according to the wireframes | colour or font attributes are not as specified. Incorrect content displayed. Incorrect sizing or layout | FF_volunteer_7 | Sean Doyle | Kyle Cheung | Amanda Elias
01_08 | Volunteer | LightHouse | 1 | PERFORMANCE | whitebox test, load the homepage in light house and test that load times are at an acceptable level. Check that image load time are acceptable. | Lighthouse returns a passing score to load times | the webpage loads slowly and lighthouse scores the performance low | FF_volunteer_8 | Sean Doyle | Kyle Cheung | Wafa Mustafa
01_09 | Volunteer | Google PageSpeed | 1 | PERFORMANCE | whitebox test, check the page performance in pagespeed insights. Ensure that performance is under the specified maximum | pagespeed insights performance all green and load times are under the specified maximum | page loads slowly. Page load takes longer than the specified maximum | FF_volunteer_9 | Sean Doyle | Kyle Cheung | Mihoko Schick
01_10 | Volunteer | JavaScript | 1 | SECURITY | dynamic test. Open up the console and check that no js errors pop up | the console is free of javascript errors | the console has javascript errors | FF_volunteer_10 | Sean Doyle | Kyle Cheung | Farshan Aslam
01_11 | Volunteer Application | Sql Injection | 1 | SECURITY | test application form to ensure that users are not able to exploit the server using sql injection | all data is validated and sanitized before before being queried by the database. | data is not sanitized, users are able to inject sql statements into the database. | FF_volunteer_11 | Sean Doyle | Kyle Cheung | Wafa Mustafa
01_12 | Volunteer Application | Application Form | 1 | USER TESTING | Ensure that all fields take appropriate values, that error messages are displayed when invalid values are used. On form submission user should be redirected to listed events | a user is able to enter their information and submit it, then be redirected to the listed events page | the form submits while incomplete or invalid data is entered. Error messages are not displayed when form validation fails | FF_volunteer_12 | Sean Doyle | Kyle Cheung | Sandra Kupfer
01_13 | Volunteer | Admin Dash | 1 | USER TESTING | ensure that as an administrator. A user is able to view all volunteer applications as well as edit, view, delete, and approve them | A user is able to edit, delete, view, and approve volunteers. All information is displayed properly, all edited and approved applications are updated correctly. | a user is unable to edit, delete, view, or approve applications or incorrect values are displayed when submitted | FF_volunteer_13 | Sean Doyle | Kyle Cheung | Amanda Elias
Note on A1: SWD: ID of item in this document, see Test Case ID column for where the Test Case Id goes.
Note on B1: SWD: The web page containing the feature being tested. E.g. about.html; /catalogue
Note on C1: SWD: Could be an area of the web page or a feature. E.g. Footer navigation; Date picker...
Note on D1: SWD: Version of the code you are testing, not the version of this document. For your final assignment it will be V1
Note on E1: SWD: Could be LAYOUT, FUNCTIONALITY, SECURITY, PERFORMANCE etc. Add your own as you feel necessary.
Note on F1: SWD: Technique & testing type(s)
Note on G1: SWD: Outcome (or range of outcomes) that occur only on success.
Note on H1: SWD: Outcome (or range of outcomes) that occur only on failure. NB: This column is not simply your Pass Criteria with the word "not" added. What is a fail?
Note on I1: SWD: The ID of the specific Test Case that addresses this issue.
Note on J1: SWD: Supervisor with Sign Off authority for this Testing Strategy.
Note on K1: SWD: The creator of the Test Case, i.e. you.
Note on L2: SWD: The name of the person expected to execute the test.